## Sheet1
Gantt Chart - Turtle Tag Project
Arthur Bondar, Benjamin Sabean
Task | Completion | Duration [Days] | Start Date | End Date
New design plan | Clear plan for new system created | 5 | 2018-05-25 | 2018-05-30
Data Recovery Attemp | Any existing Informating extracted form USB disk | 1 | 2018-05-30 | 2018-05-31
Software for Timing controller | Timing controller can communicate with Raspberry Pi computer | 2 | 2018-06-01 | 2018-06-03
Software for GPS | Raspberry Pi can communicated succesfully with the GPS module | 2 | 2018-06-02 | 2018-06-04
Printer Circuit Board design | PCB Designed | 2 | 2018-06-03 | 2018-06-05
Printer Circuit Board made | PCB Printed and soldered n NSCC | 1 | 2018-06-05 | 2018-06-06
Full Software Intergration | Different pieces of software integrated for final testing | 2 | 2018-06-07 | 2018-06-09
PCB Testing | PCB is tested with the software | 4 | 2018-06-08 | 2018-06-12
Electronics Support platform | Platform for electronics and batteries inside eclosure designed using 3D modeling software | 2 | 2018-06-13 | 2018-06-15
Support platform printed | Printed using 3D printer in NSCC | 1 | 2018-06-15 | 2018-06-16
Charging circuit test | New battery charging circuit integration and testing | 1 | 2018-06-16 | 2018-06-17
Fully assembly | Fist unit is fully assembled | 1 | 2018-06-17 | 2018-06-18
Testing and Tourbleshooting | Testing system performance over days of recording | 8 | 2018-06-18 | 2018-06-26
Second Unit Assmebly | Make PCB and assemble second unit | 7 | 2018-06-19 | 2018-06-26
Final Adjustments | Make neccesary corrections and final adjustmets to software/hardware | 5 | 2018-06-26 | 2018-07-01